## Sheet1
Task | Status | Estimated Timeline | Assigned To
Requirements of the 3rd Phase of the EMS/TMS development
Payroll section development. frontend | In Progress | 2 day | Snehal
Payroll section development. Backend | In Progress | 2 Day | Adesh
Updates in HR/Company policy section. | Pending | 2 day | Snehal
Delayed tasks escalation In case of task delayed by the team mates of any leader or the manager, he should be able to raise the issue to the appropriate authorities. The emails should be triggered to the employee and the higher authorities. | Pending | 2 day | Adesh
In case of the task delayed from IT support, the employee should be able to raise a concern by escalating the matter to the appropriate authorities by initiating the emails from the apps. The 'Escalate' (Button) should be there to initiate the automatic mails. | Pending | 2 day | Snehal
Birthday wishing emails | Completed | - | -
Minutes of Meeting discus Task
Regularization requests will be approved only by Admin and HR. Managers and Team Leads will have view-only access. | Pending | 2 hr | Adesh
Evaluate and integrate multiple Maps APIs to fetch a more accurate employee location. | Pending | 2 day | Adesh
Display the employee checkout location on both the Admin and Employee. | Completed | - | Snehal
Leave requests will be approved only by the Manager. Email notifications should be sent to the Manager, with Admin, HR, CEO and MD included in CC. | Completed | - | Snehal
Read the First Policy, provide mandatory acknowledgment and then allow employees to view the next Company Policy. | Completed | - | Adesh
Add an option in the Admin panel to revert old employee registrations. | Completed | - | Snehal
Capture the employee's photo during the Check-In process. | Completed | - | Adesh